## Slide 1
iTalent Execution & Rollout Plan
51Talk Egypt · HRBP: Ahmed Elsadek · March 2026
Transitioning 51Talk Egypt leave management from email to iTalent ESS Portal

## Slide 2
Guiding Principles
Four principles to ensure a safe transition
🚫 No Big Bang
Pilot first, fix issues, then expand
📂 No Data Loss
All historical leave balances imported before go-live
⚡ No Disruption
Parallel run ensures no employee is left without a process
🔔 No Surprises
Employees and managers trained before they see the system

## Slide 3
6-Week Rollout Timeline
Phased, low-risk approach from configuration to full operations
Week 1
Configure & Setup
Week 2
Integrate & Notify
Week 3
Pilot Go-Live
Week 4
Evaluate & Fix
Week 5–6
Full Rollout
Month 2+
Operations

## Slide 4
Stage 0: Prerequisites (2–3 Days)
Must complete before any configuration begins
Task | Owner | Duration
Confirm iTalent admin access | HRBP + IT Admin | 2–3 days
Export employee master data from Attendance Dashboard | HRBP | Day 1
Collect org chart / reporting lines for all teams | HRBP | Day 1
Pilot department confirmed: CC Team | Management ✅ | Completed
Get manager email list for approval chain setup | HRBP | Day 2
Backup current leave sheet used in Attendance Dashboard | HRBP | Day 1
🚨 Admin access is on the critical path — every day of delay pushes pilot and rollout back by 1 day.

## Slide 5
Stage 1A: Fix Leave Types (Day 1–2)
Rename placeholders, set entitlements, fix UI typos
Action | In iTalent | Expected Result
Rename "Leave Item 6" | Admin → Attendance → Leave Config | Name becomes "Casual Leave"
Rename "Leave Item 34" | Admin → Attendance → Leave Config | Name becomes "Marriage Leave"
Fix "Leave Applictaion" typo | Admin → Menu Config (2 locations) | Correct spelling in sidebar
Set Annual Leave entitlement | Leave Config → Annual Leave → Balance Rule | 15 days (<1yr) / 21 days (≥1yr)
Set Sick Leave pay rate | Leave Config → Sick Leave | 75% salary, attachment required
Set Maternity Leave | Leave Config → Maternity | 120 days, 1yr service required
Set Paternity Leave | Leave Config → Paternity | 3 occurrences max, 1 day each
Set Unpaid Leave | Leave Config → Unpaid | No limit, dual approval

## Slide 6
Stage 1B: Approval Workflows (Day 2–3)
Three workflow templates covering all leave types
Workflow A "Single Approval"
Manager Only
Leave Types: Casual Leave Paternity Bereavement Business Trips
Workflow B "HR Reviewed"
Manager → HR
Leave Types: Sick Leave Maternity Marriage Miscarriage
Workflow C "Full Chain"
Manager → Director → HR
Leave Types: Annual Leave > 3 days Unpaid Leave

## Slide 7
Stage 2: Attendance Dashboard Integration (Week 2)
Connect iTalent leave exports to the Streamlit Attendance Dashboard
Step | Action | Validation
1 | Configure iTalent leave export (vertical format: CRM ¦ Date ¦ Leave Type ¦ Status) | Export file generates correctly
2 | Export sample approved leaves from iTalent | Approved only, correct date range
3 | Import into Attendance Dashboard leave sheet | No import errors
4 | Run Dashboard report — verify penalties correct | 0 discrepancies vs manual sheet
5 | Confirm leave code mapping (AL, SL, CL, ML, PL, UL, BL, MAL, MCL) | All codes recognized
6 | Document Monthly SOP for HR | SOP reviewed and approved
📅 Export trigger: Manual — HR runs on 21st of each month | Format: Excel (.xlsx) | Date range: 21st prev → 20th current

## Slide 8
Stage 3: Employee Data Migration (Week 2)
Import master data and set opening leave balances before any employee logs in
Field | Source | Notes
Employee ID (AC-No / PS ID) | Attendance Dashboard | Must match Dashboard master
CRM | Attendance Dashboard | Links leave records to attendance
Full Name | Attendance Dashboard | —
Department | Attendance Dashboard | —
Join Date | HR records | Critical — drives annual leave entitlement (15 vs 21 days)
Vendor | Attendance Dashboard | Just HR / Migrate
National ID | HR records | —
Manager / Approver | Org chart | Linked to workflow routing
Email Address | Company directory | Needed for notification delivery

## Slide 9
Stage 4: Pilot — CC Team (Week 3)
Validate full workflow in real conditions before company-wide rollout
Day 1 Monday
• Kickoff
• Brief pilot manager
• Share employee quick-start guide
• Enable CC Team in iTalent
Day 2–3
• Live Usage
• Employees submit pending leave requests
• Manager approves via My Approval
• HRBP monitors for issues
Day 4
• Mid-Pilot Check
• Review all submissions
• Verify: notifications, approvals, balances
• Fix any issues found
Day 5 Friday
• Pilot Review
• Debrief with pilot manager
• Document all issues
• Go / No-Go decision for full rollout

## Slide 10
Stage 5 & 6: Fix, Train & Full Rollout (Week 4–6)
Training sessions, parallel run, and cutover from email to iTalent
Session | Audience | Duration | Content
Manager Training | All team managers | 1 hour | My Approval, Process Delegation, Batch Approval
Employee Training | All staff | 30 min | Leave Application, My Attendance, My Profile
HR Operations | HR team | 1 hour | Monthly export process, balance management, reports
Week 5: Training for all managers (Day 1) → Training for all employees by department (Day 2–3) → Employees begin submitting in iTalent (Day 4–5)
Week 6: Parallel run — employees submit in BOTH email + iTalent. HR approves in both. End of week: compare logs → confirm consistency.
End of Week 6: Email process retired. HR email auto-reply updated. All pending requests migrated to iTalent.

## Slide 11
Risk Register
Known risks and mitigations for a safe transition
Risk | Likelihood | Impact | Mitigation
Employees don't know how to use the system | High | Medium | Training + quick-start guide + HR support
Manager approval bottleneck | Medium | High | Process Delegation configured; 48hr escalation
Leave balance errors at import | Medium | High | Verify 5 sample employees before import
Dashboard not recognizing iTalent leave codes | Low | High | Test export-import before pilot starts
Employee not in iTalent system | Low | Medium | Full audit of employee list before go-live
Manager rejects system adoption | Low | High | Escalate to Director; demo system value
System downtime during critical period | Low | Medium | Backup: revert to email process temporarily

## Slide 12
Success Metrics & Contact
How we measure a successful rollout
Metric | Target | Measurement
Leave requests via iTalent | 100% within 4 weeks of cutover | Count of email requests received after cutover
Approval turnaround time | < 24 hours | iTalent approval timestamps
Leave data accuracy in Dashboard | 0 discrepancies | Compare iTalent export vs old leave sheet
Employee satisfaction with ESS | > 80% positive | Short survey after 1 month
HR time saved on leave admin | > 2 hours/week | HR self-reported
Contact: Ahmed Elsadek | hr.egy@51talk.com · System: 51talk.italent.cn · Based on: 51Talk Egypt Employee Handbook + Attendance Dashboard v2.2